## Project Schedule
Start Date | 2016-01-01
|  |  |  | Duration |  |  |  | Best Case |  |  | Expected |  |  | Worst Case |  |  | MC Simulation |  |  | MC Analysis
Project ID | Task ID | Name | Dependencies | Best | Expected | Worst | Sample | Start | End |  | Start | End |  | Start | End |  | Start | End |  | Min | Max | Mean | R2 | Rank
A |  | Planning
| A.100 | Construction Plan |  | 15 | 30 | 45 | 21 | 2016-01-01 | 2016-01-16 | 15 | 2016-01-01 | 2016-01-31 | 30 | 2016-01-01 | 2016-02-15 | 45 | 2016-01-01 | 2016-01-22 | 21 | 16 | 44 | 30.006 | 4.563% | 6 | 21.36%
| A.200 | Hiring Plan |  | 15 | 30 | 45 | 34 | 2016-01-01 | 2016-01-16 | 15 | 2016-01-01 | 2016-01-31 | 30 | 2016-01-01 | 2016-02-15 | 45 | 2016-01-01 | 2016-02-04 | 34 | 16 | 44 | 30.002 | 2.67% | 8 | 16.34%
| A.300 | Plan Review | A.100, A.200 | 10 | 15 | 30 | 17 | 2016-01-17 | 2016-01-27 | 10 | 2016-02-01 | 2016-02-16 | 15 | 2016-02-16 | 2016-03-17 | 30 | 2016-02-05 | 2016-02-22 | 17 | 10 | 28 | 16.664 | 4.337% | 7 | 20.82%
B |  | Construction
| B.100 | Construction: Task 1 | A.300 | 60 | 90 | 120 | 90 | 2016-01-28 | 2016-03-28 | 60 | 2016-02-17 | 2016-05-17 | 90 | 2016-03-18 | 2016-07-16 | 120 | 2016-02-23 | 2016-05-23 | 90 | 62 | 118 | 89.997 | 5.892% | 5 | 24.27%
| B.200 | Construction: Task 2 | A.300 | 60 | 90 | 120 | 106 | 2016-01-28 | 2016-03-28 | 60 | 2016-02-17 | 2016-05-17 | 90 | 2016-03-18 | 2016-07-16 | 120 | 2016-02-23 | 2016-06-08 | 106 | 61 | 118 | 89.996 | 10.71% | 4 | 32.72%
| B.300 | Construction: Task 3 | A.300 | 30 | 45 | 100 | 53 | 2016-01-28 | 2016-02-27 | 30 | 2016-02-17 | 2016-04-02 | 45 | 2016-03-18 | 2016-06-26 | 100 | 2016-02-23 | 2016-04-16 | 53 | 30 | 92 | 51.67 | 0.4347% | 10 | 6.593%
C |  | Review
| C.100 | Construction Review | B.100,B.200,B.300 | 15 | 30 | 60 | 29 | 2016-03-29 | 2016-04-13 | 15 | 2016-05-18 | 2016-06-17 | 30 | 2016-07-17 | 2016-09-15 | 60 | 2016-06-09 | 2016-07-08 | 29 | 16 | 56 | 32.501 | 20.67% | 3 | 45.46%
| C.200 | Internal Review | A.300 | 15 | 30 | 60 | 24 | 2016-01-28 | 2016-02-12 | 15 | 2016-02-17 | 2016-03-18 | 30 | 2016-03-18 | 2016-05-17 | 60 | 2016-02-23 | 2016-03-18 | 24 | 16 | 56 | 32.5 | 0.08045% | 11 | -2.836%
| C.300 | Compliance Review | C.100, A.300 | 15 | 30 | 60 | 40 | 2016-04-14 | 2016-04-29 | 15 | 2016-06-18 | 2016-07-18 | 30 | 2016-09-16 | 2016-11-15 | 60 | 2016-07-09 | 2016-08-18 | 40 | 15 | 57 | 32.499 | 21.98% | 2 | 46.89%
| C.400 | Compliance / Completion | C.200, C.300 | 15 | 30 | 60 | 34 | 2016-04-30 | 2016-05-15 | 15 | 2016-07-19 | 2016-08-18 | 30 | 2016-11-16 | 2017-01-15 | 60 | 2016-08-19 | 2016-09-22 | 34 | 16 | 57 | 32.501 | 24.56% | 1 | 49.56%
| C.500 | Project Review | C.200, C.400 | 10 | 15 | 20 | 15 | 2016-05-16 | 2016-05-26 | 10 | 2016-08-19 | 2016-09-03 | 15 | 2017-01-16 | 2017-02-05 | 20 | 2016-09-23 | 2016-10-08 | 15 | 10 | 20 | 14.998 | 0.9443% | 9 | 9.717%
Completion Date | [8 empty] | 2016-05-26 | 146 |  | 2016-09-03 | 246 |  | 2017-02-05 | 401 |  | 2016-10-08 | 281 | 203 | 337 | 265.114
Formulas:
Best Case = 1 + MAX( L7, [End, row above], )
End = [Best Case] + [Duration]
End = [Expected] + [Expected]
Expected = 1 + MAX( P7, [End, row above], )
Worst Case = 1 + MAX( T7, [End, row above], )
MC Simulation = 1 + MAX( X7, [End, row above], )

## Report
Construction Plan | Plan Review |  | Construction: Task 1 |  | Construction Review
Hiring Plan |  |  | Construction: Task 2
Construction: Task 3
[6 empty] | Compliance Review | Compliance / Completion
|  |  | Internal Review |  |  |  |  | Project Review
Original Model |  | Days | Date
Expected Completion |  | 246 | 2016-09-03
Best-Case |  | 146 | 2016-05-26
Worst-Case |  | 401 | 2017-02-05
Probability Analysis |  | Days | Date | Probability
Completion within "Expected" |  | 246 | 2016-09-03 | 16.4%
- within 10% overrun |  | 271 | 2016-09-28 | 62.8%
- within 20% overrun |  | 296 | 2016-10-23 | 95.4%
Minimum |  | 203 | 2016-07-22
Maximum |  | 337 | 2016-12-03
Average |  | 265.114 | 2016-09-22 02:44
Confidence Ranges |  | Days | Date
75% Confidence |  | 278 | 2016-10-05
80% Confidence |  | 281 | 2016-10-08
90% Confidence |  | 289 | 2016-10-16
Formulas:
Construction: Task 1 = [Days]+projectStartDate

## Tables
Histogram Data |  |  | Sorted R2 Values
Completion Time | Probability | Cumulative | Index | Row | Label | Value
210 | 0% | 0% | 11 | 12 | Internal Review | 0.08045%
217 | 0.2% | 0% | 10 | 8 | Construction: Task 3 | 0.4347%
224 | 0.3% | 0.2% | 9 | 15 | Project Review | 0.9443%
231 | 2% | 0.5% | 8 | 2 | Hiring Plan | 2.67%
238 | 5.1% | 2.5% | 7 | 3 | Plan Review | 4.337%
245 | 7.6% | 7.6% | 6 | 1 | Construction Plan | 4.563%
252 | 9.4% | 15.2% | 5 | 6 | Construction: Task 1 | 5.892%
259 | 14.8% | 24.6% | 4 | 7 | Construction: Task 2 | 10.71%
266 | 14.7% | 39.4% | 3 | 11 | Construction Review | 20.67%
273 | 12.4% | 54.1% | 2 | 13 | Compliance Review | 21.98%
280 | 12.3% | 66.5% | 1 | 14 | Compliance / Completion | 24.56%
287 | 9% | 78.8%
294 | 6.5% | 87.8%
301 | 2.9% | 94.3%
308 | 1.7% | 97.2%
315 | 0.5% | 98.9%
322 | 0.4% | 99.4%
329 | 0% | 99.8%
336 | 0% | 99.8%
343 | 0.1% | 99.8%